## Timeline
Timeline for Sponsored Project Submissions
Proposal Due to: | What's Due: | When Due: | Date Required:
Sponsor | Complete proposal | Enter due date here: | 2019-10-05
Research Office | Completed PeopleSoft (RO System) Complete Proposal in Agency's Portal (Cayuse, ProposalCentral, etc.) | 3 business days prior to Sponsor due date | 2019-10-02
Sponsored Program Coordinator | Project Narrative, Bio Sketches, Current & Pending forms, Sub Award Documents, any additional sponsor requirements | 7 working days prior to due date | 2019-09-26
Sponsored Program Coordinator | Abstract, Budget, Budget Justification, Provider Category Determination worksheet for Vendor/Sub/Consultants, Sub Award Budgets/Contact information | 2 weeks prior to due date | 2019-09-23
Sponsored Program Coordinator | Notification | 3-4 weeks prior to due date | 2019-09-09
Formulas:
Date Required: = WORKDAY([Date Required:, row above],-3,0)

## NIH Documents
Check: | Documents: | Page limits | Due Date: | To: | Notes
| Notify SPC of intention to submit and provide FOA number/link |  | ASAP | SPC | 4 weeks minimum notice
| Project Summary/Abstract | 30 lines | 2019-09-23 | SPC | Web form can begin routing for Institutional approvals
| UD Budget |  | 2019-09-23 | SPC
| Budget Justification |  | 2019-09-23 | SPC
| Sub Award Documents (SPC to obtain required documents) |  | 2019-09-23 | SPC
| Bio Sketches (UD & Subs) |  | 2019-09-26 | SPC
| Current & Pending (mentors & co-mentors only) | 3 | 2019-09-26 | SPC
| Cover Letter (if required) |  | 2019-09-26 | SPC
| Intro to Application (for resubmissions & revision) *Federal Indentification Number (FIN) required by PI | 1 | 2019-09-26 | SPC
| Multiple PD/PI Leadership Plan (if applicable) |  | 2019-09-26 | SPC
| Project Narrative | 3 sentences | 2019-09-26 | SPC
| Bibliography & References Cited |  | 2019-09-26 | SPC
| Facilites & Other Resources |  | 2019-09-26 | SPC
| Equipment |  | 2019-09-26 | SPC
Human Subjects NIH Policy
| Human Subjects & Clinical Trials Form |  | 2019-09-26 | SPC
| Protection of Human Subjects |  | 2019-09-26 | SPC
| Inclusion of Women & Minorities |  | 2019-09-26 | SPC
| Inclusion of Children |  | 2019-09-26 | SPC
| Recruitment and Retention Plan |  | 2019-09-26 | SPC
| Study Timeline |  | 2019-09-26 | SPC
| Data and Safety Monitoring Plan |  | 2019-09-26 | SPC
| Overall Structure of the Study Team |  | 2019-09-26 | SPC
| Statistical Design and Power |  | 2019-09-26 | SPC
| Dissemination Plan |  | 2019-09-26 | SPC
| PHS Inclusion Enrollment Report |  | 2019-09-26 | SPC
| Other Clinical Trial-related attachments (if application) |  | 2019-09-26 | SPC
| Progress Report Publication List (as applicable) |  | 2019-09-26 | SPC
| Vertebrate Animals (if Vertebrate Animals = yes) |  | 2019-09-26 | SPC
| Candidate Information and Goals for Career Development |  | 2019-09-26 | SPC
| Training in the Responsible Conduct of Research |  | 2019-09-26 | SPC
| Candidates Plan to Provide Mentoring |  | 2019-09-26 | SPC
| Plans and Statements of Mentor and Co-Mentor(s) |  | 2019-09-26 | SPC
| Letters of Support |  | 2019-09-26 | SPC
| Description of Institutional Environment |  | 2019-09-26 | SPC
| Institutional Commitment to Candidate's Research Career Development |  | 2019-09-26 | SPC
| Data/Resource Sharing Plan |  | 2019-09-26 | SPC
| Consortium/Contractual Arrangements |  | 2019-09-26 | SPC
| Authenticiation of Key Biological and/or Chemical Resources (only required when project will involve key biological and/or chemical resources) |  | 2019-09-26 | SPC
| Appendices |  | 2019-09-26 | SPC
| PHS Assignment Request form |  | 2019-09-23 | SPC
| Research Strategy | check FOA | 2019-09-26 | SPC
| Specific Aims | 1 | 2019-09-26 | SPC
| Routing of Cayuse proposal for PI approvals |  | 2019-10-02 | HARD DEADLINE | Cayuse Routing
| Research Office Review of proposals |  | 10/2/2019 - 10/5/2019
| Submission to NIH |  | 2019-10-05
**Note - if any date falls on a weekend, documents will be due the Friday before
check FOA
5

## Budget
PI Name:
Title: | [15 empty] | Inflation Rate | 1.02
Dates: | [15 empty] | NIH salary cap | 192300
Sponsor:
PS Grants:
|  |  | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 | YEAR 1 BASE SALARY (ANNUALIZED)
|  |  | 2019-07-01 |  | 2020-07-01 |  | 2021-07-01 |  | 2022-07-01 |  | 2023-07-01
PERSONNEL |  | Annualized Effort | 2020-06-30 |  | 2021-06-30 |  | 2022-06-30 |  | 2023-06-30 |  | 2024-06-30 |  | COST-SHARED EFFORT (Including salary > NIH Cap)
| PM |  |  | YR2 |  | YR3 |  | YR4 |  | YR5 |  |  |  |  | PM | Annualized Effort
Faculty/Professional |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Faculty/Professional |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Effort | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | % effort | 0 | 0% | 0 | 0 | 0 | 0 | 0
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 40.6% fringe benefits |  |  | 0 | 0 | 0 | 0 | 0
[17 empty] | 0 | 0 | 0 | 0 | 0
summer ninths | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | Total Annuallized Academic Effort | 0 | 0%
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Total Annualized Summer Effort | 0 | 0%
[14 empty] | Total Annual Effort | 0 | 0%
Faculty/Professional |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Faculty/Professional
Effort | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | % effort | 0 | 0% | 0 | 0 | 0 | 0 | 0
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 40.6% fringe benefits |  |  | 0 | 0 | 0 | 0 | 0
[14 empty] | Total Annuallized Academic Effort | 0 | 0% | 0 | 0 | 0 | 0 | 0
summer ninths | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | Total Annualized Summer Effort | 0 | 0%
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Total Annual Effort | 0 | 0%
Faculty/Professional
Faculty/Professional |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | % effort | 0 | 0% | 0 | 0 | 0 | 0 | 0
Effort | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | 40.6% fringe benefits |  |  | 0 | 0 | 0 | 0 | 0
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Total Annuallized Academic Effort | 0 | 0% | 0 | 0 | 0 | 0 | 0
[14 empty] | Total Annualized Summer Effort | 0 | 0%
Faculty/Professional |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Total Annual Effort | 0 | 0%
Effort | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Faculty/Professional |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Effort | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Faculty/Professional |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Effort | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Faculty/Professional |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Effort | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Misc Wage
Effort |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Current rates:
7.1% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | https://grants.nih.gov/grants/guide/notice-files/NOT-OD-18-175.html
Graduate student(s) |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 21000 | (Insert YR1 base 9-month grad amount)
11.9% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | # of Months (i.e. 9 academic, 3 summer) | 12 | $21,000 as of 9/1/18
[14 empty] | # of Grad Students (Yr1) | 0
[14 empty] | # of Grad Students (Yr2) | 0
[14 empty] | # of Grad Students (Yr3) | 0
SUBTOTAL PERSONNEL |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | # of Grad Students (Yr4) | 0
[14 empty] | # of Grad Students (Yr5) | 0
CONSULTANTS
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
SUBTOTAL CONSULTANTS |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TRAVEL
Conference travel |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
SUBTOTAL TRAVEL |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
SUPPLIES and EXPENSE
< > |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
< > |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Participant Compensation |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Vendor/Fee for service |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Publication Costs |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Misc supplies |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Equipment <$5,000
Participant Support (F&A n/a)
Equipment >$5,000 (F&A n/a)
SUBTOTAL SUPPLIES and EXPENSE |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TUITION |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[14 empty] | 2019-2020 nonresident tuition: | 34160
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 6832
SUBCONTRACTS
Institution Name
total amount |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
direct cost |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
idc amount |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Subcontract subject to IDC |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Institution Name
total amount |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
direct cost |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
idc amount |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Subcontract subject to IDC |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Institution Name
total amount |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
direct cost |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
idc amount |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Subcontract subject to IDC |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
SUBTOTAL SUBCONTRACTS |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TOTAL DIRECT COSTS |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TOTAL DIRECT COSTS LESS SUB IDC |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TOTAL DIRECT COSTS SUBJECT TO IDC |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
INDIRECT COSTS (7/1/19) | 0.595 | 6 | 0 |  | 0 |  | 0 |  | 0 |  | 0
INDIRECT COSTS (7/1/20) | 0.6 | 6 | 0
TOTAL SPONSOR REQUEST |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Fringe Benefits (valid 7/1/19 - 6/30/20)
Faculty and Professional Fringe Rate: | 0.406
Salaried Staff Fringe Rate: | 0.597
Graduate Student Fringe Rate: | 0.119
Supp Professional/Misc. Wage/FICA: | 0.071
Formulas:
Year 2 = [Year 1, row below]+1
Year 2 = [Year 2, row above]+364
Year 3 = [Year 2, row below]+1
Year 3 = [Year 3, row above]+364
Year 4 = [Year 3, row below]+1
Year 4 = [Year 4, row above]+364
Year 5 = [Year 4, row below]+1
Year 5 = [Year 5, row above]+365

## lists (hidden)
Years | Not yet recruiting | Anticipated | Treatment | USA | USA: United States of America | 840
Months | Recruiting | Actual | Prevention | AFG | AFG: Afghanistan | 4
Weeks | Enrolling by invitation |  | Diagnostics | ALA | ALA: Aland Islands | 248
Days | Active, not recruiting |  | Supportive Care | ALB | ALB: Albania | 8
Hours | Completed |  | Screening | DZA | DZA: Algeria | 12
Minutes | Suspended |  | Health services research | ASM | ASM: American Samoa | 16
| Terminated (Halted Prematurely) |  | Basic Science | AND | AND: Andorra | 20
| Withdrawan (No participants enrolled) |  | Device Feasibility | AGO | AGO: Angola | 24
|  |  | Other | AIA | AIA: Anguilla | 660
|  |  |  | ATA | ATA: Antarctica | 10
| Early Phase 1 (or Phase 0) | Single group | N/A | ATG | ATG: Antigua and Barbuda | 28
| Phase 1 | Parallel | Randomized | ARG | ARG: Argentina | 32
| Phase 1/2 | Cross-over | Not-Randomized | ARM | ARM: Armenia | 51
| Phase 2 | Factorial |  | ABW | ABW: Aruba | 533
| Phase 2/3 | Sequential |  | AUS | AUS: Australia | 36
| Phase 3 | Other |  | AUT | AUT: Austria | 40
| Phase 4 |  |  | AZE | AZE: Azerbaijan | 31
| Other |  |  | BHS | BHS:Bahamas | 44
|  |  |  | BHR | BHR: Bahrain | 48
|  |  |  | BGD | BGD: Bangladesh | 50
|  |  |  | BRB | BRB: Barbados | 52
|  |  |  | BLR | BLR: Belarus | 112
|  |  |  | BEL | BEL: Belgium | 56
|  |  |  | BLZ | BLZ: Belize | 84
|  |  |  | BEN | BEN: Benin | 204
|  |  |  | BMU | BMU: Bermuda | 60
|  |  |  | BTN | BTN: Bhutan | 64
|  |  |  | BOL | BOL: Bolivia (Plurinational State of) | 68
|  |  |  | BES | BES: Bonaire, Sint Eustatius and Saba | 535
|  |  |  | BIH | BIH: Bosnia and Herzegovina | 70
|  |  |  | BWA | BWA: Botswana | 72
|  |  |  | BVT | BVT: Bouvet Island | 74
|  |  |  | BRA | BRA: Brazil | 76
|  |  |  | IOT | IOT: British Indian Ocean Territory | 86
|  |  |  | VGB | VGB: British Virgin Islands | 92
|  |  |  | BRN | BRN: Brunei Darussalam | 96
|  |  |  | BGR | BGR: Bulgaria | 100
|  |  |  | BFA | BFA: Burkina Faso | 854
|  |  |  | BDI | BDI: Burundi | 108
|  |  |  | CPV | CPV: Cabo Verde | 132
|  |  |  | KHM | KHM: Cambodia | 116
|  |  |  | CMR | CMR: Cameroon | 120
|  |  |  | CAN | CAN: Canada | 124
|  |  |  | CYM | CYM: Cayman Islands | 136
|  |  |  | CAF | CAF: Central African Republic | 140
|  |  |  | TCD | TCD: Chad | 148
|  |  |  | CHL | CHL: Chile | 152
|  |  |  | CHN | CHN: China | 156
|  |  |  | HKG | HKG: China, Hong Kong Special Administrative Region | 344
|  |  |  | MAC | MAC: China, Macao Special Administrative Region | 446
|  |  |  | CXR | CXR: Christmas Island | 162
|  |  |  | CCK | CCK: Cocos (Keeling) Islands | 166
|  |  |  | COL | COL: Colombia | 170
|  |  |  | COM | COM: Comoros | 174
|  |  |  | COG | COG: Congo | 178
|  |  |  | COK | COK: Cook Islands | 184
|  |  |  | CRI | CRI: Costa Rica | 188
|  |  |  | CIV | CIV: Côte d'Ivoire | 384
|  |  |  | HRV | HRV: Croatia | 191
|  |  |  | CUB | CUB: Cuba | 192
|  |  |  | CUW | CUW: Curaçao | 531
|  |  |  | CYP | CYP: Cyprus | 196
|  |  |  | CZE | CZE: Czechia | 203
|  |  |  | PRK | PRK: Democratic People's Republic of Korea | 408
|  |  |  | COD | COD: Democratic Republic of the Congo | 180
|  |  |  | DNK | DNK: Denmark | 208
|  |  |  | DJI | DJI: Djibouti | 262
|  |  |  | DMA | DMA: Dominica | 212
|  |  |  | DOM | DOM: Dominican Republic | 214
|  |  |  | ECU | ECU: Ecuador | 218
|  |  |  | EGY | EGY: Egypt | 818
|  |  |  | SLV | SLV: El Salvador | 222
|  |  |  | GNQ | GNQ: Equatorial Guinea | 226
|  |  |  | ERI | ERI: Eritrea | 232
|  |  |  | EST | EST: Estonia | 233
|  |  |  | SWZ | SWZ: Eswatini | 748
|  |  |  | ETH | ETH: Ethiopia | 231
|  |  |  | FLK | FLK: Falkland Islands (Malvinas) | 238
|  |  |  | FRO | FRO: Faroe Islands | 234
|  |  |  | FJI | FJI: Fiji | 242
|  |  |  | FIN | FIN: Finland | 246
|  |  |  | FRA | FRA: France | 250
|  |  |  | GUF | GUF: French Guiana | 254
|  |  |  | PYF | PYF: French Polynesia | 258
|  |  |  | ATF | ATF: French Southern Territories | 260
|  |  |  | GAB | GAB: Gabon | 266
|  |  |  | GMB | GMB: Gambia | 270
|  |  |  | GEO | GEO: Georgia | 268
|  |  |  | DEU | DEU: Germany | 276
|  |  |  | GHA | GHA: Ghana | 288
|  |  |  | GIB | GIB: Gibraltar | 292
|  |  |  | GRC | GRC: Greece | 300
|  |  |  | GRL | GRL: Greenland | 304
|  |  |  | GRD | GRD: Grenada | 308
|  |  |  | GLP | GLP: Guadeloupe | 312
|  |  |  | GUM | GUM: Guam | 316
|  |  |  | GTM | GTM: Guatemala | 320
|  |  |  | GGY | GGY: Guernsey | 831
|  |  |  | GIN | GIN: Guinea | 324
|  |  |  | GNB | GNB: Guinea-Bissau | 624
|  |  |  | GUY | GUY: Guyana | 328
|  |  |  | HTI | HTI: Haiti | 332
|  |  |  | HMD | HMD: Heard Island and McDonald Islands | 334
|  |  |  | VAT | VAT: Holy See | 336
|  |  |  | HND | HND: Honduras | 340
|  |  |  | HUN | HUN: Hungary | 348
|  |  |  | ISL | ISL: Iceland | 352
|  |  |  | IND | IND: India | 356
|  |  |  | IDN | IND: Indonesia | 360
|  |  |  | IRN | IRN: Iran (Islamic Republic of) | 364
|  |  |  | IRQ | IRQ: Iraq | 368
|  |  |  | IRL | IRL: Ireland | 372
|  |  |  | IMN | IMN: Isle of Man | 833
|  |  |  | ISR | ISR: Israel | 376
|  |  |  | ITA | ITA: Italy | 380
|  |  |  | JAM | JAM: Jamaica | 388
|  |  |  | JPN | JPN: Japan | 392
|  |  |  | JEY | JEY: Jersey | 832
|  |  |  | JOR | JOR: Jordan | 400
|  |  |  | KAZ | KAZ: Kazakhstan | 398
|  |  |  | KEN | KEN: Kenya | 404
|  |  |  | KIR | KIR: Kiribati | 296
|  |  |  | KWT | KWT: Kuwait | 414
|  |  |  | KGZ | KGZ: Kyrgyzstan | 417
|  |  |  | LAO | LAO: Lao People's Democratic Republic | 418
|  |  |  | LVA | LVA: Latvia | 428
|  |  |  | LBN | LBN: Lebanon | 422
|  |  |  | LSO | LSO: Lesotho | 426
|  |  |  | LBR | LBR: Liberia | 430
|  |  |  | LBY | LBY: Libya | 434
|  |  |  | LIE | LIE: Liechtenstein | 438
|  |  |  | LTU | LTU: Lithuania | 440
|  |  |  | LUX | LUX: Luxembourg | 442
|  |  |  | MDG | MDG: Madagascar | 450
|  |  |  | MWI | MWI: Malawi | 454
|  |  |  | MYS | MYS: Malaysia | 458
|  |  |  | MDV | MDV: Maldives | 462
|  |  |  | MLI | MLI: Mali | 466
|  |  |  | MLT | MLT: Malta | 470
|  |  |  | MHL | MHL: Marshall Islands | 584
|  |  |  | MTQ | MTQ: Martinique | 474
|  |  |  | MRT | MRT: Mauritania | 478
|  |  |  | MUS | MUS: Mauritius | 480
|  |  |  | MYT | MYT: Mayotte | 175
|  |  |  | MEX | MEX: Mexico | 484
|  |  |  | FSM | FAM: Micronesia (Federated States of) | 583
|  |  |  | MCO | MCO: Monaco | 492
|  |  |  | MNG | MNG: Mongolia | 496
|  |  |  | MNE | MNE: Montenegro | 499
|  |  |  | MSR | MSR: Montserrat | 500
|  |  |  | MAR | MAR: Morocco | 504
|  |  |  | MOZ | MOZ: Mozambique | 508
|  |  |  | MMR | MMR: Myanmar | 104
|  |  |  | NAM | NAM: Namibia | 516
|  |  |  | NRU | NRU: Nauru | 520
|  |  |  | NPL | NPL: Nepal | 524
|  |  |  | NLD | NLD: Netherlands | 528
|  |  |  | NCL | NCL: New Caledonia | 540
|  |  |  | NZL | NZL: New Zealand | 554
|  |  |  | NIC | NIC: Nicaragua | 558
|  |  |  | NER | NER: Niger | 562
|  |  |  | NGA | NGA: Nigeria | 566
|  |  |  | NIU | NIU: Niue | 570
|  |  |  | NFK | NFK: Norfolk Island | 574
|  |  |  | MNP | MNP: Northern Mariana Islands | 580
|  |  |  | NOR | NOR: Norway | 578
|  |  |  | OMN | OMN: Oman | 512
|  |  |  | PAK | PAK: Pakistan | 586
|  |  |  | PLW | PLW: Palau | 585
|  |  |  | PAN | PAN: Panama | 591
|  |  |  | PNG | PNG: Papua New Guinea | 598
|  |  |  | PRY | PRY: Paraguay | 600
|  |  |  | PER | PER: Peru | 604
|  |  |  | PHL | PHL: Philippines | 608
|  |  |  | PCN | PCN: Pitcairn | 612
|  |  |  | POL | POL: Poland | 616
|  |  |  | PRT | PRT: Portugal | 620
|  |  |  | PRI | PRI: Puerto Rico | 630
|  |  |  | QAT | QAT: Qatar | 634
|  |  |  | KOR | KOR: Republic of Korea | 410
|  |  |  | MDA | MDA: Republic of Moldova | 498
|  |  |  | REU | REU: Réunion | 638
|  |  |  | ROU | ROU: Romania | 642
|  |  |  | RUS | RUS: Russian Federation | 643
|  |  |  | RWA | RWA: Rwanda | 646
|  |  |  | BLM | BLM: Saint Barthélemy | 652
|  |  |  | SHN | SHN: Saint Helena | 654
|  |  |  | KNA | KNA: Saint Kitts and Nevis | 659
|  |  |  | LCA | LCA: Saint Lucia | 662
|  |  |  | MAF | MAF: Saint Martin (French Part) | 663
|  |  |  | SPM | SPM: Saint Pierre and Miquelon | 666
|  |  |  | VCT | VCT: Saint Vincent and the Grenadines | 670
|  |  |  | WSM | WSM: Samoa | 882
|  |  |  | SMR | SMR: San Marino | 674
|  |  |  | STP | STP: Sao Tome and Principe | 678
[5 empty] | Sark | 680
|  |  |  | SAU | SAU: Saudi Arabia | 682
|  |  |  | SEN | SEN: Senegal | 686
|  |  |  | SRB | SRB: Serbia | 688
|  |  |  | SYC | SYC: Seychelles | 690
|  |  |  | SLE | SLE: Sierra Leone | 694
|  |  |  | SGP | SGP: Singapore | 702
|  |  |  | SXM | SXM: Sint Maarten (Dutch part) | 534
|  |  |  | SVK | SVK: Slovakia | 703
|  |  |  | SVN | SVN: Slovenia | 705
|  |  |  | SLB | SLB: Solomon Islands | 90
|  |  |  | SOM | SOM: Somalia | 706
|  |  |  | ZAF | ZAF: South Africa | 710
|  |  |  | SGS | SGS: South Georgia and the South Sandwich Islands | 239
|  |  |  | SSD | SSD: South Sudan | 728
|  |  |  | ESP | ESP: Spain | 724
|  |  |  | LKA | LKA: Sri Lanka | 144
|  |  |  | PSE | PSE: State of Palestine | 275
|  |  |  | SDN | SDN: Sudan | 729
|  |  |  | SUR | SUR: Suriname | 740
|  |  |  | SJM | SJM: Svalbard and Jan Mayen Islands | 744
|  |  |  | SWE | SWE: Sweden | 752
|  |  |  | CHE | CHE: Switzerland | 756
|  |  |  | SYR | SYR: Syrian Arab Republic | 760
|  |  |  | TJK | TJK: Tajikistan | 762
|  |  |  | THA | THA: Thailand | 764
|  |  |  | MKD | MKD: The former Yugoslav Republic of Macedonia | 807
|  |  |  | TLS | TLS: Timor-Leste | 626
|  |  |  | TGO | TGO: Togo | 768
|  |  |  | TKL | TKL: Tokelau | 772
|  |  |  | TON | TON: Tonga | 776
|  |  |  | TTO | TTO: Trinidad and Tobago | 780
|  |  |  | TUN | TUN: Tunisia | 788
|  |  |  | TUR | TUR: Turkey | 792
|  |  |  | TKM | TKM: Turkmenistan | 795
|  |  |  | TCA | TCA: Turks and Caicos Islands | 796
|  |  |  | TUV | TUV: Tuvalu | 798
|  |  |  | UGA | UGA: Uganda | 800
|  |  |  | UKR | UKR: Ukraine | 804
|  |  |  | ARE | ARE: United Arab Emirates | 784
|  |  |  | GBR | GBR: United Kingdom of Great Britain and Northern Ireland | 826
|  |  |  | TZA | TZA: United Republic of Tanzania | 834
|  |  |  | UMI | UMI: United States Minor Outlying Islands | 581
|  |  |  | VIR | VIR: United States Virgin Islands | 850
|  |  |  | URY | URY: Uruguay | 858
|  |  |  | UZB | UZB: Uzbekistan | 860
|  |  |  | VUT | BUT: Vanuatu | 548
|  |  |  | VEN | VEN: Venezuela (Bolivarian Republic of) | 862
|  |  |  | VNM | VNM: Viet Nam | 704
|  |  |  | WLF | WLF: Wallis and Futuna Islands | 876
|  |  |  | ESH | ESH: Western Sahara | 732
|  |  |  | YEM | YEM: Yemen | 887
|  |  |  | ZMB | ZMB: Zambia | 894
|  |  |  | ZWE | ZWE: Zimbabwe | 716
|  |  |  | USA | USA: United States of America | 840