## Timeline
Timeline for Sponsored Project Submissions
Proposal Due to: | What's Due: | When Due: | Date Required:
Sponsor | Complete proposal | Enter due date here: | 2019-10-05
Research Office | Completed PeopleSoft (RO System) Complete Proposal in Agency's Portal (Cayuse, ProposalCentral, etc.) | 72 hours prior to Sponsor due date | 2019-10-02
Sponsored Program Coordinator | Project Narrative, Bio Sketches, Current & Pending forms, Sub Award Documents, any additional sponsor requirements | 7 working days prior to due date | 2019-09-26
Sponsored Program Coordinator | Abstract, Budget, Budget Justification, Provider Category Determination worksheet for Vendor/Sub/Consultants, Sub Award Budgets/Contact information | 2 weeks prior to due date | 2019-09-23
Sponsored Program Coordinator | Notification | 3-4 weeks prior to due date | 2019-09-09
Formulas:
Date Required: = WORKDAY([Date Required:, row above],-3,0)

## NIH Documents
Check: | Documents: | Page limits | Due Date: | To: | Notes
| Notify SPC of intention to submit and provide FOA number/link |  | ASAP | SPC | 4 weeks minimum notice
| Project Summary/Abstract | 30 lines | 2019-09-23 | SPC | Web form can begin routing for Institutional approvals
| UD Budget |  | 2019-09-23 | SPC
| Budget Justification |  | 2019-09-23 | SPC
| Sub Award Documents (SPC to obtain required documents) |  | 2019-09-23 | SPC
| Bio Sketches (UD & Subs) |  | 2019-09-26 | SPC
| Current/Pending/Complete (all Key Personnel, when applicable) |  | 2019-09-26 | SPC
| Cover Letter (if required) |  | 2019-09-26 | SPC
| Intro to Application (for resubmissions & revision) *Federal Indentification Number (FIN) required by PI | 1 | 2019-09-26 | SPC
| Multiple PD/PI Leadership Plan (if applicable) |  | 2019-09-26 | SPC
| Project Narrative | 3 sentences | 2019-09-26 | SPC
| Bibliography & References Cited |  | 2019-09-26 | SPC
| Facilites & Other Resources |  | 2019-09-26 | SPC
| Equipment |  | 2019-09-26 | SPC
| Human Subjects NIH Policy |  |  |  |  | Note: For Dissemination Plan on Human Subjects form (model language from IRB): The principal investigator will ensure that clinical trial(s) are registered and that results information is submitted to ClinicalTrials.gov as required. The University of Delaware has implemented detailed guidelines and procedures to safeguard compliance with all terms and conditions of the award, including those in place for clinical trials.
| Human Subjects & Clinical Trials Form |  | 2019-09-26 | SPC
| Protection of Human Subjects |  | 2019-09-26 | SPC
| Inclusion of Women & Minorities |  | 2019-09-26 | SPC
| Inclusion of Children |  | 2019-09-26 | SPC
| Recruitment and Retention Plan |  | 2019-09-26 | SPC
| Study Timeline |  | 2019-09-26 | SPC
| Data and Safety Monitoring Plan |  | 2019-09-26 | SPC
| Overall Structure of the Study Team |  | 2019-09-26 | SPC
| Statistical Design and Power |  | 2019-09-26 | SPC
| Dissemination Plan |  | 2019-09-26 | SPC
| PHS Inclusion Enrollment Report |  | 2019-09-26 | SPC
| Other Clinical Trial-related attachments (if application) |  | 2019-09-26 | SPC
| Progress Report Publication List (as applicable) |  | 2019-09-26 | SPC
| Vertebrate Animals (if Vertebrate Animals = yes) |  | 2019-09-26 | SPC
| Letters of Support |  | 2019-09-26 | SPC
| Data/Resource Sharing Plan |  | 2019-09-26 | SPC
| Consortium/Contractual Arrangements |  | 2019-09-26 | SPC
| Authenticiation of Key Biological and/or Chemical Resources (only required when project will involve key biological and/or chemical resources) |  | 2019-09-26 | SPC
| Appendices |  | 2019-09-26 | SPC
| PHS Assignment Request form |  | 2019-09-23 | SPC
| Research Strategy | check FOA | 2019-09-26 | SPC
| Specific Aims | 1 | 2019-09-26 | SPC
| Routing of Cayuse proposal for PI approvals |  | 2019-10-02 | HARD DEADLINE | Cayuse Routing
| Research Office Review of proposals |  | 10/2/2019 - 10/5/2019
| Submission to NIH |  | 2019-10-05
**Note - if any date falls on a weekend, documents will be due the Friday before
check FOA
5

## Budget
PI Name:
Title: | [15 empty] | Inflation Rate | 1.02
Dates: | [15 empty] | NIH salary cap | 192300
Sponsor:
PS Grants:
|  |  | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 | YEAR 1 BASE SALARY (ANNUALIZED)
|  |  | 2019-07-01 |  | 2020-07-01 |  | 2021-07-01 |  | 2022-07-01 |  | 2023-07-01
PERSONNEL |  | Annualized Effort | 2020-06-30 |  | 2021-06-30 |  | 2022-06-30 |  | 2023-06-30 |  | 2024-06-30 |  | COST-SHARED EFFORT (Including salary > NIH Cap)
| PM |  |  | YR2 |  | YR3 |  | YR4 |  | YR5 |  |  |  |  | PM | Annualized Effort
Faculty/Professional |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Faculty/Professional |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Effort | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | % effort | 0 | 0% | 0 | 0 | 0 | 0 | 0
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 40.6% fringe benefits |  |  | 0 | 0 | 0 | 0 | 0
[17 empty] | 0 | 0 | 0 | 0 | 0
summer ninths | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | Total Annuallized Academic Effort | 0 | 0%
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Total Annualized Summer Effort | 0 | 0%
[14 empty] | Total Annual Effort | 0 | 0%
Faculty/Professional |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Faculty/Professional
Effort | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | % effort | 0 | 0% | 0 | 0 | 0 | 0 | 0
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 40.6% fringe benefits |  |  | 0 | 0 | 0 | 0 | 0
[14 empty] | Total Annuallized Academic Effort | 0 | 0% | 0 | 0 | 0 | 0 | 0
summer ninths | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | Total Annualized Summer Effort | 0 | 0%
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Total Annual Effort | 0 | 0%
Faculty/Professional
Faculty/Professional |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | % effort | 0 | 0% | 0 | 0 | 0 | 0 | 0
Effort | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | 40.6% fringe benefits |  |  | 0 | 0 | 0 | 0 | 0
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Total Annuallized Academic Effort | 0 | 0% | 0 | 0 | 0 | 0 | 0
[14 empty] | Total Annualized Summer Effort | 0 | 0%
Faculty/Professional |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Total Annual Effort | 0 | 0%
Effort | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Faculty/Professional |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Effort | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Faculty/Professional |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Effort | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Faculty/Professional |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Effort | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
40.6% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Misc Wage
Effort |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | Current rates:
7.1% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | https://grants.nih.gov/grants/guide/notice-files/NOT-OD-18-175.html
Graduate student(s) |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 21000 | (Insert YR1 base 9-month grad amount)
11.9% fringe benefits |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | # of Months (i.e. 9 academic, 3 summer) | 12 | $21,000 as of 9/1/18
[14 empty] | # of Grad Students (Yr1) | 0
[14 empty] | # of Grad Students (Yr2) | 0
[14 empty] | # of Grad Students (Yr3) | 0
SUBTOTAL PERSONNEL |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | # of Grad Students (Yr4) | 0
[14 empty] | # of Grad Students (Yr5) | 0
CONSULTANTS
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
SUBTOTAL CONSULTANTS |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TRAVEL
Conference travel |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
SUBTOTAL TRAVEL |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
SUPPLIES and EXPENSE
< > |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
< > |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Participant Compensation |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Vendor/Fee for service |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Publication Costs |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Misc supplies |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Equipment <$5,000
Participant Support (F&A n/a)
Equipment >$5,000 (F&A n/a)
SUBTOTAL SUPPLIES and EXPENSE |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TUITION |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[14 empty] | 2019-2020 nonresident tuition: | 34160
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 6832
SUBCONTRACTS
Institution Name
total amount |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
direct cost |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
idc amount |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Subcontract subject to IDC |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Institution Name
total amount |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
direct cost |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
idc amount |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Subcontract subject to IDC |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Institution Name
total amount |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
direct cost |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
idc amount |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Subcontract subject to IDC |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
SUBTOTAL SUBCONTRACTS |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TOTAL DIRECT COSTS |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TOTAL DIRECT COSTS LESS SUB IDC |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TOTAL DIRECT COSTS SUBJECT TO IDC |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
INDIRECT COSTS (7/1/19) | 0.595 | 6 | 0 |  | 0 |  | 0 |  | 0 |  | 0
INDIRECT COSTS (7/1/20) | 0.6 | 6 | 0
TOTAL SPONSOR REQUEST |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Fringe Benefits (valid 7/1/19 - 6/30/20)
Faculty and Professional Fringe Rate: | 0.406
Salaried Staff Fringe Rate: | 0.597
Graduate Student Fringe Rate: | 0.119
Supp Professional/Misc. Wage/FICA: | 0.071
Formulas:
Year 2 = [Year 1, row below]+1
Year 2 = [Year 2, row above]+364
Year 3 = [Year 2, row below]+1
Year 3 = [Year 3, row above]+364
Year 4 = [Year 3, row below]+1
Year 4 = [Year 4, row above]+364
Year 5 = [Year 4, row below]+1
Year 5 = [Year 5, row above]+365

## Approvals
PROPOSAL APPROVALS | PROPOSED FIRST-YEAR TOTAL (DIRECTS & INDIRECTS)
Principal Investigator (P.I.), Chairperson, and Research Office | Up to $500,000
P.I., Chairperson, Dean, and Research Office | Up to $1,000,000
P.I., Chairperson, Dean, Research Office, and Provost | Up to $2,000,000
P.I., Chairperson, Dean, Research Office, Provost, and President | Over $2,000,000
All proposals that include a waiver of indirect costs must be signed by the Dean
or their designee.
AWARD APPROVALS | TOTAL AWARD (DIRECTS & INDIRECTS)
P.I., Research Office | Up to $1,000,000
P.I., Research Office, and Provost | Up to $2,000,000
P.I., Research Office, and President | Over $2,000,000

## lists (hidden)
Years | Not yet recruiting | Anticipated | Treatment | USA | USA: United States of America | 840
Months | Recruiting | Actual | Prevention | AFG | AFG: Afghanistan | 4
Weeks | Enrolling by invitation |  | Diagnostics | ALA | ALA: Aland Islands | 248
Days | Active, not recruiting |  | Supportive Care | ALB | ALB: Albania | 8
Hours | Completed |  | Screening | DZA | DZA: Algeria | 12
Minutes | Suspended |  | Health services research | ASM | ASM: American Samoa | 16
| Terminated (Halted Prematurely) |  | Basic Science | AND | AND: Andorra | 20
| Withdrawan (No participants enrolled) |  | Device Feasibility | AGO | AGO: Angola | 24
|  |  | Other | AIA | AIA: Anguilla | 660
|  |  |  | ATA | ATA: Antarctica | 10
| Early Phase 1 (or Phase 0) | Single group | N/A | ATG | ATG: Antigua and Barbuda | 28
| Phase 1 | Parallel | Randomized | ARG | ARG: Argentina | 32
| Phase 1/2 | Cross-over | Not-Randomized | ARM | ARM: Armenia | 51
| Phase 2 | Factorial |  | ABW | ABW: Aruba | 533
| Phase 2/3 | Sequential |  | AUS | AUS: Australia | 36
| Phase 3 | Other |  | AUT | AUT: Austria | 40
| Phase 4 |  |  | AZE | AZE: Azerbaijan | 31
| Other |  |  | BHS | BHS:Bahamas | 44
|  |  |  | BHR | BHR: Bahrain | 48
|  |  |  | BGD | BGD: Bangladesh | 50
|  |  |  | BRB | BRB: Barbados | 52
|  |  |  | BLR | BLR: Belarus | 112
|  |  |  | BEL | BEL: Belgium | 56
|  |  |  | BLZ | BLZ: Belize | 84
|  |  |  | BEN | BEN: Benin | 204
|  |  |  | BMU | BMU: Bermuda | 60
|  |  |  | BTN | BTN: Bhutan | 64
|  |  |  | BOL | BOL: Bolivia (Plurinational State of) | 68
|  |  |  | BES | BES: Bonaire, Sint Eustatius and Saba | 535
|  |  |  | BIH | BIH: Bosnia and Herzegovina | 70
|  |  |  | BWA | BWA: Botswana | 72
|  |  |  | BVT | BVT: Bouvet Island | 74
|  |  |  | BRA | BRA: Brazil | 76
|  |  |  | IOT | IOT: British Indian Ocean Territory | 86
|  |  |  | VGB | VGB: British Virgin Islands | 92
|  |  |  | BRN | BRN: Brunei Darussalam | 96
|  |  |  | BGR | BGR: Bulgaria | 100
|  |  |  | BFA | BFA: Burkina Faso | 854
|  |  |  | BDI | BDI: Burundi | 108
|  |  |  | CPV | CPV: Cabo Verde | 132
|  |  |  | KHM | KHM: Cambodia | 116
|  |  |  | CMR | CMR: Cameroon | 120
|  |  |  | CAN | CAN: Canada | 124
|  |  |  | CYM | CYM: Cayman Islands | 136
|  |  |  | CAF | CAF: Central African Republic | 140
|  |  |  | TCD | TCD: Chad | 148
|  |  |  | CHL | CHL: Chile | 152
|  |  |  | CHN | CHN: China | 156
|  |  |  | HKG | HKG: China, Hong Kong Special Administrative Region | 344
|  |  |  | MAC | MAC: China, Macao Special Administrative Region | 446
|  |  |  | CXR | CXR: Christmas Island | 162
|  |  |  | CCK | CCK: Cocos (Keeling) Islands | 166
|  |  |  | COL | COL: Colombia | 170
|  |  |  | COM | COM: Comoros | 174
|  |  |  | COG | COG: Congo | 178
|  |  |  | COK | COK: Cook Islands | 184
|  |  |  | CRI | CRI: Costa Rica | 188
|  |  |  | CIV | CIV: Côte d'Ivoire | 384
|  |  |  | HRV | HRV: Croatia | 191
|  |  |  | CUB | CUB: Cuba | 192
|  |  |  | CUW | CUW: Curaçao | 531
|  |  |  | CYP | CYP: Cyprus | 196
|  |  |  | CZE | CZE: Czechia | 203
|  |  |  | PRK | PRK: Democratic People's Republic of Korea | 408
|  |  |  | COD | COD: Democratic Republic of the Congo | 180
|  |  |  | DNK | DNK: Denmark | 208
|  |  |  | DJI | DJI: Djibouti | 262
|  |  |  | DMA | DMA: Dominica | 212
|  |  |  | DOM | DOM: Dominican Republic | 214
|  |  |  | ECU | ECU: Ecuador | 218
|  |  |  | EGY | EGY: Egypt | 818
|  |  |  | SLV | SLV: El Salvador | 222
|  |  |  | GNQ | GNQ: Equatorial Guinea | 226
|  |  |  | ERI | ERI: Eritrea | 232
|  |  |  | EST | EST: Estonia | 233
|  |  |  | SWZ | SWZ: Eswatini | 748
|  |  |  | ETH | ETH: Ethiopia | 231
|  |  |  | FLK | FLK: Falkland Islands (Malvinas) | 238
|  |  |  | FRO | FRO: Faroe Islands | 234
|  |  |  | FJI | FJI: Fiji | 242
|  |  |  | FIN | FIN: Finland | 246
|  |  |  | FRA | FRA: France | 250
|  |  |  | GUF | GUF: French Guiana | 254
|  |  |  | PYF | PYF: French Polynesia | 258
|  |  |  | ATF | ATF: French Southern Territories | 260
|  |  |  | GAB | GAB: Gabon | 266
|  |  |  | GMB | GMB: Gambia | 270
|  |  |  | GEO | GEO: Georgia | 268
|  |  |  | DEU | DEU: Germany | 276
|  |  |  | GHA | GHA: Ghana | 288
|  |  |  | GIB | GIB: Gibraltar | 292
|  |  |  | GRC | GRC: Greece | 300
|  |  |  | GRL | GRL: Greenland | 304
|  |  |  | GRD | GRD: Grenada | 308
|  |  |  | GLP | GLP: Guadeloupe | 312
|  |  |  | GUM | GUM: Guam | 316
|  |  |  | GTM | GTM: Guatemala | 320
|  |  |  | GGY | GGY: Guernsey | 831
|  |  |  | GIN | GIN: Guinea | 324
|  |  |  | GNB | GNB: Guinea-Bissau | 624
|  |  |  | GUY | GUY: Guyana | 328
|  |  |  | HTI | HTI: Haiti | 332
|  |  |  | HMD | HMD: Heard Island and McDonald Islands | 334
|  |  |  | VAT | VAT: Holy See | 336
|  |  |  | HND | HND: Honduras | 340
|  |  |  | HUN | HUN: Hungary | 348
|  |  |  | ISL | ISL: Iceland | 352
|  |  |  | IND | IND: India | 356
|  |  |  | IDN | IND: Indonesia | 360
|  |  |  | IRN | IRN: Iran (Islamic Republic of) | 364
|  |  |  | IRQ | IRQ: Iraq | 368
|  |  |  | IRL | IRL: Ireland | 372
|  |  |  | IMN | IMN: Isle of Man | 833
|  |  |  | ISR | ISR: Israel | 376
|  |  |  | ITA | ITA: Italy | 380
|  |  |  | JAM | JAM: Jamaica | 388
|  |  |  | JPN | JPN: Japan | 392
|  |  |  | JEY | JEY: Jersey | 832
|  |  |  | JOR | JOR: Jordan | 400
|  |  |  | KAZ | KAZ: Kazakhstan | 398
|  |  |  | KEN | KEN: Kenya | 404
|  |  |  | KIR | KIR: Kiribati | 296
|  |  |  | KWT | KWT: Kuwait | 414
|  |  |  | KGZ | KGZ: Kyrgyzstan | 417
|  |  |  | LAO | LAO: Lao People's Democratic Republic | 418
|  |  |  | LVA | LVA: Latvia | 428
|  |  |  | LBN | LBN: Lebanon | 422
|  |  |  | LSO | LSO: Lesotho | 426
|  |  |  | LBR | LBR: Liberia | 430
|  |  |  | LBY | LBY: Libya | 434
|  |  |  | LIE | LIE: Liechtenstein | 438
|  |  |  | LTU | LTU: Lithuania | 440
|  |  |  | LUX | LUX: Luxembourg | 442
|  |  |  | MDG | MDG: Madagascar | 450
|  |  |  | MWI | MWI: Malawi | 454
|  |  |  | MYS | MYS: Malaysia | 458
|  |  |  | MDV | MDV: Maldives | 462
|  |  |  | MLI | MLI: Mali | 466
|  |  |  | MLT | MLT: Malta | 470
|  |  |  | MHL | MHL: Marshall Islands | 584
|  |  |  | MTQ | MTQ: Martinique | 474
|  |  |  | MRT | MRT: Mauritania | 478
|  |  |  | MUS | MUS: Mauritius | 480
|  |  |  | MYT | MYT: Mayotte | 175
|  |  |  | MEX | MEX: Mexico | 484
|  |  |  | FSM | FAM: Micronesia (Federated States of) | 583
|  |  |  | MCO | MCO: Monaco | 492
|  |  |  | MNG | MNG: Mongolia | 496
|  |  |  | MNE | MNE: Montenegro | 499
|  |  |  | MSR | MSR: Montserrat | 500
|  |  |  | MAR | MAR: Morocco | 504
|  |  |  | MOZ | MOZ: Mozambique | 508
|  |  |  | MMR | MMR: Myanmar | 104
|  |  |  | NAM | NAM: Namibia | 516
|  |  |  | NRU | NRU: Nauru | 520
|  |  |  | NPL | NPL: Nepal | 524
|  |  |  | NLD | NLD: Netherlands | 528
|  |  |  | NCL | NCL: New Caledonia | 540
|  |  |  | NZL | NZL: New Zealand | 554
|  |  |  | NIC | NIC: Nicaragua | 558
|  |  |  | NER | NER: Niger | 562
|  |  |  | NGA | NGA: Nigeria | 566
|  |  |  | NIU | NIU: Niue | 570
|  |  |  | NFK | NFK: Norfolk Island | 574
|  |  |  | MNP | MNP: Northern Mariana Islands | 580
|  |  |  | NOR | NOR: Norway | 578
|  |  |  | OMN | OMN: Oman | 512
|  |  |  | PAK | PAK: Pakistan | 586
|  |  |  | PLW | PLW: Palau | 585
|  |  |  | PAN | PAN: Panama | 591
|  |  |  | PNG | PNG: Papua New Guinea | 598
|  |  |  | PRY | PRY: Paraguay | 600
|  |  |  | PER | PER: Peru | 604
|  |  |  | PHL | PHL: Philippines | 608
|  |  |  | PCN | PCN: Pitcairn | 612
|  |  |  | POL | POL: Poland | 616
|  |  |  | PRT | PRT: Portugal | 620
|  |  |  | PRI | PRI: Puerto Rico | 630
|  |  |  | QAT | QAT: Qatar | 634
|  |  |  | KOR | KOR: Republic of Korea | 410
|  |  |  | MDA | MDA: Republic of Moldova | 498
|  |  |  | REU | REU: Réunion | 638
|  |  |  | ROU | ROU: Romania | 642
|  |  |  | RUS | RUS: Russian Federation | 643
|  |  |  | RWA | RWA: Rwanda | 646
|  |  |  | BLM | BLM: Saint Barthélemy | 652
|  |  |  | SHN | SHN: Saint Helena | 654
|  |  |  | KNA | KNA: Saint Kitts and Nevis | 659
|  |  |  | LCA | LCA: Saint Lucia | 662
|  |  |  | MAF | MAF: Saint Martin (French Part) | 663
|  |  |  | SPM | SPM: Saint Pierre and Miquelon | 666
|  |  |  | VCT | VCT: Saint Vincent and the Grenadines | 670
|  |  |  | WSM | WSM: Samoa | 882
|  |  |  | SMR | SMR: San Marino | 674
|  |  |  | STP | STP: Sao Tome and Principe | 678
[5 empty] | Sark | 680
|  |  |  | SAU | SAU: Saudi Arabia | 682
|  |  |  | SEN | SEN: Senegal | 686
|  |  |  | SRB | SRB: Serbia | 688
|  |  |  | SYC | SYC: Seychelles | 690
|  |  |  | SLE | SLE: Sierra Leone | 694
|  |  |  | SGP | SGP: Singapore | 702
|  |  |  | SXM | SXM: Sint Maarten (Dutch part) | 534
|  |  |  | SVK | SVK: Slovakia | 703
|  |  |  | SVN | SVN: Slovenia | 705
|  |  |  | SLB | SLB: Solomon Islands | 90
|  |  |  | SOM | SOM: Somalia | 706
|  |  |  | ZAF | ZAF: South Africa | 710
|  |  |  | SGS | SGS: South Georgia and the South Sandwich Islands | 239
|  |  |  | SSD | SSD: South Sudan | 728
|  |  |  | ESP | ESP: Spain | 724
|  |  |  | LKA | LKA: Sri Lanka | 144
|  |  |  | PSE | PSE: State of Palestine | 275
|  |  |  | SDN | SDN: Sudan | 729
|  |  |  | SUR | SUR: Suriname | 740
|  |  |  | SJM | SJM: Svalbard and Jan Mayen Islands | 744
|  |  |  | SWE | SWE: Sweden | 752
|  |  |  | CHE | CHE: Switzerland | 756
|  |  |  | SYR | SYR: Syrian Arab Republic | 760
|  |  |  | TJK | TJK: Tajikistan | 762
|  |  |  | THA | THA: Thailand | 764
|  |  |  | MKD | MKD: The former Yugoslav Republic of Macedonia | 807
|  |  |  | TLS | TLS: Timor-Leste | 626
|  |  |  | TGO | TGO: Togo | 768
|  |  |  | TKL | TKL: Tokelau | 772
|  |  |  | TON | TON: Tonga | 776
|  |  |  | TTO | TTO: Trinidad and Tobago | 780
|  |  |  | TUN | TUN: Tunisia | 788
|  |  |  | TUR | TUR: Turkey | 792
|  |  |  | TKM | TKM: Turkmenistan | 795
|  |  |  | TCA | TCA: Turks and Caicos Islands | 796
|  |  |  | TUV | TUV: Tuvalu | 798
|  |  |  | UGA | UGA: Uganda | 800
|  |  |  | UKR | UKR: Ukraine | 804
|  |  |  | ARE | ARE: United Arab Emirates | 784
|  |  |  | GBR | GBR: United Kingdom of Great Britain and Northern Ireland | 826
|  |  |  | TZA | TZA: United Republic of Tanzania | 834
|  |  |  | UMI | UMI: United States Minor Outlying Islands | 581
|  |  |  | VIR | VIR: United States Virgin Islands | 850
|  |  |  | URY | URY: Uruguay | 858
|  |  |  | UZB | UZB: Uzbekistan | 860
|  |  |  | VUT | BUT: Vanuatu | 548
|  |  |  | VEN | VEN: Venezuela (Bolivarian Republic of) | 862
|  |  |  | VNM | VNM: Viet Nam | 704
|  |  |  | WLF | WLF: Wallis and Futuna Islands | 876
|  |  |  | ESH | ESH: Western Sahara | 732
|  |  |  | YEM | YEM: Yemen | 887
|  |  |  | ZMB | ZMB: Zambia | 894
|  |  |  | ZWE | ZWE: Zimbabwe | 716
|  |  |  | USA | USA: United States of America | 840