## Sheet1
Item | Task | Begin Date | Due Date | Communication
Comp Time Balances for Non-Exempt | * Provide list to Departments to review and determine if balance should be paid or recouped | 2020-04-28 | 2020-05-15 | * Coordinate with HR Liaisons
Balances | * Confirm accuracy of sick and vacation balances. * If shadow system exists, that information will need to be collected as well. | 2020-05-18 | 2020-06-19 | * Coordinate with Timekeepers and/or HR Managers.
Leave Request Form | * Employees will not be able to enter Leave Requests for time after 8/31 * Form will no longer be used to request time off | Mid-May July 20th | n/a | * Working at UD Newsletter (May, June & July) * Website (FAQ)
Additional Assignment Form | * Improvements to form are implemented | Mid-July | n/a | * Working at UD Newsletter (July) * Website
Time Off Balance View | * Ability for employees to view Historical Leave Requests with a link to the new system. * Balances will no longer be present. | July-end | n/a | * Working at UD Newsletter (July) * Website (FAQ)
Department Table Updates | * Update table to reflect HR Managers and College Business Officers * We are coordinating a mass load with IT | Mid-June | Mid-July | * HR Systems will make necessary updates to this table
Supervisor Changes | * Submit Supervisor Form for changes to Timekeeper 3 Role identifying NEW Reporter Role (where applicable) * Possible mass load coordinated with IT as well | Mid-July | July-end | * Coordinate with HR Managers and CBO's
Access to Old System | * Access will still be needed for reference/historical purposes * Pay Adjustments prior to 8/9 (Project Team is working through these details (more information to be shared at a later date) | July-end | n/a | * Additional information provided to Focus Groups